## Springboot
Sr No | Task | Sub tasks | Definition of done | Expected time for task completion(no of days & 10 hrs per day) | Start date | End date
1 | Creating repos in github and permission setup |  |  | 0.25
2 | Distribution of services among team members |  |  | 0.25
3 | Setting up of gateway |  | a)All routes must be configured b)Token validation should be handled. Gateway must talk to Authentication & Authorization service for token validation | 1
4 | Setting up of eureka server |  |  | 0.5
5 | MongoDb setup as docker container |  |  | 0.5
6 | MySql setup as docker container |  |  | 0.5
7 | ELK setup as docker container
8 | SonarQube setup |  | Jococo plugin should be installed | 0.5
9 | User service implementation | Create User | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/createUser should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
10 |  | Update user | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/updateUser should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branchi)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
11 |  | Delete user | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/deleteUser should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
12 |  | List users | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getUsers should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.75
13 |  | Get user details | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getUserDetails should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
14 | Accounts service implementation | Create account | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/createAccount should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Update account | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/updateAccount should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Delete account | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/deleteAccount should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | List account | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getAccounts should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Get account details | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getAccountDetails should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.75
15 | Balance service implementation | Create balance | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/creeateBalance should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Update balance | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/updateBalance should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Delete balance | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/deleteBalance should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | List balance | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getBalances should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Get balance details | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getBalanceDetail should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
16 | Transaction service implementation | Create transaction | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/createTransaction should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Update transaction | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/updateTransaction should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Delete transaction | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/deleteTransaction should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | List transaction | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getTransaction should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
|  | Get transaction details | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/getTransactionDetail should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. Collection should be there g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.5
17 | Authentication & Authorization service | /signup | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/signup should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. Collection should be there g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 1
18 |  | /login | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/login should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. Collection should be there g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.75
19 |  | /validate-token | a)Unit test cases with 80% coverage b)No critical or major sonarqube errors c)Separate branch feature/validate-token should be there d)Error handling(Exception) e)Integration with API gateway f)Postman testing with all positive and negative scenarios. Collection should be there g)Response should be as per swagger spec h)ELK integration for loggin.Print request and response logs and error logs i)Pull request been raised, peer and mentor code review been done and branch successfully merged to develop branch | 0.75
20 | Containerisation of all the services |  | Each service must have a dockerfile to run the springboot application as docker continers | 0.5
21 | Peer code review |  | Everyday one hour to be done of peer code reviews. 1 hr * 10 days = 10 hrs | 1
22 | Review comment rework |  | Everyday one hour for addressing review comments | 1
|  |  | Total man days | 19

## References
Techstack | Reference material link
Springboot | https://www.nginx.com/blog/introduction-to-microservices/
https://martinfowler.com/articles/microservices.html
https://swagger.io/resources/articles/best-practices-in-api-design/
https://stackoverflow.blog/2020/03/02/best-practices-for-rest-api-design/
https://developer.mozilla.org/en-US/docs/Web/HTTP/Status
https://www.youtube.com/playlist?list=PLTyWtrsGknYegrUmDZB6rcqMotOFZKvbn
https://www.youtube.com/playlist?list=PLwvrYc43l1Mwqpf9i-1B1gXfMeHOm6DeY
https://spring.io/why-spring
https://spring.io/microservices
https://spring.io/projects/spring-boot
Angular
ReactJs